## Sheet1
Description | Evaluation | Probability | Impact Level | Responsibility | Response | Control Measures | Probability post implementation | Impact Level post implementation | Control Measures post implementation
User information about figures failure to be added | Data not added | medium | medium | David | user sends a message to inform of the problem and David responds to the problem and adds the data | set up correct pathways so information added correctly
User information being changed by other users | Data changed | medium | high | David | user sends a message to inform of the problem and David responds to the problem and returns the data to original state | create users so people log in have their own database
The website unable to be accessed | Website down | low | high | David | user sends a message to inform of the problem and David responds to the problem and puts website back up | use Gunicorn to set up multiple bots to the page so if one goes down the site can still be accessed
Data added incorrectly (wrong position) | Data incorrect | low | medium | David | user sends a message to inform of the problem and David responds to the problem and adds the data correctly | set up correct pathways so information added correctly
Data added wrongly by user | Data incorrect | medium | low | User and David | user sends a message to inform of the problem and david responds to the problem and adds the data correctly | make sure the user is informed correctly about where to add data
The website being slow as multiple people try to use it | Slow or down website | medium | medium | David | add more space increase sever space/ number of bots/ limit the numbers on the page | use Gunicorn to set up multiple bots to hand a large amount of people
Data being stolen or changed due to Database details released | Data stolen or changed | medium | high | David | assessing the impact and changing username and passwords as well as changing the position of the database | using environment variables and setting secret text in Jenkins | low | high | adding more multi-factor authentication
Data being stolen or changed due to secret key being released | Data stolen or changed | medium | high | David | assessing the impact and changing username and passwords as well as changing the position of the database | using environment variables and setting secret text in Jenkins | low | high | adding more multi-factor authentication
Someone using Jenkins to change or steal data | Data stolen or changed | medium | high | David | assess the damage and change passwords and usernames | limit Jenkins to only the processes it needs and not full access
CSRF attack | Data stolen or changed | medium | high | David | assessing the impact and changing username and passwords as well as changing the position of the database | using form.hidden_tag() and SECRET_KEY from WTForms | low | high | adding more multi-factor authentication
VM for sever goes down | loss of service and data | low | high | David | user sends a message to inform of the problem and restart/ start a new sever copying any lost data | all code push to a external repository so easily accessed if machine goes down | low | medium | create a backup VM with everything needed installed
VM for database goes down | loss of service and data | low | high | David | user sends a message to inform of the problem and restart/ start a new sever copying any lost data | Take regular backups of the database
VM for Jenkins goes down | loss of service and data | low | high | David | user sends a message to inform of the problem and restart/ start a new sever copying any lost data | script saved in the code pushed to the repository | low | medium | set up a backup Jenkins server with run code added